## Sheet
Division | Action Items | Deliverables | Development & Assignment of Deliverables | Management Approval | Commissioner's Approval | Published or Completed | Reason for Delay (Divisional) | Presented & Approved at the Commission's Meeting | Finalized at Commission Level | Reason for Delay (Commision)
PRS SUPPORTED BY FMS, | Feeder Nomenclature | Updated name of feeders and assets - TCN | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS SUPPORTED BY FMS, | Feeder Nomenclature | Updated name of feeders and assets - DisCos | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS SUPPORTED BY FMS, | Feeder Nomenclature | Hosting of centralised NESI asset database - NERC/UKNAIF | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS SUPPORTED BY FMS, | Feeder Nomenclature | Issunace of NESI nomenclature order (for go-forward) - NERC | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS | Strategic plan implementation | Refined MS project reporting process | TRUE | FALSE | FALSE | FALSE |  | FALSE | FALSE | None
PRS | Strategic plan implementation | Weighting of deliverables to drive independent assesment of progress | TRUE | FALSE | FALSE | FALSE |  | FALSE | FALSE | None
PRS | Strategic plan implementation | Quartely Commission Progress update | TRUE | FALSE | FALSE | FALSE |  | FALSE | FALSE | None
PRS | Strategic plan implementation | End of year performance appraisal | TRUE | FALSE | FALSE | FALSE |  | FALSE | FALSE | None
PRS | Strategic plan implementation | Peer review workshop | TRUE | FALSE | FALSE | FALSE |  | FALSE | FALSE | None
PRS | Strategic plan implementation | 2024 - 2026 strategic plan with a clear M&E framework | TRUE | FALSE | FALSE | FALSE |  | FALSE | FALSE | None
PRS SUPPORTED BY CA, | General Analytical support | Framework for dealing with DisCo insecurity claims | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS SUPPORTED BY CA, | General Analytical support | Energy situation room report (support EPM) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS SUPPORTED BY CA, | General Analytical support | SBT situation room report (support EPM) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS SUPPORTED BY CA, | General Analytical support | Implementation of Capping Regulation (support CA) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS SUPPORTED BY CA, | General Analytical support | Analytics component for the public information (support CO) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS | DAP II - Microsoft 365 + IoT based data acquisition | Web forms for data collection | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS | DAP II - Microsoft 365 + IoT based data acquisition | Automated Dashboard | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS | DAP II - Microsoft 365 + IoT based data acquisition | Operationalisation of Intranet System (Mini-ERP) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS | DAP II - Microsoft 365 + IoT based data acquisition | Publishing and hosting of real-time grid performance on NERC website - GenCos IoT | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS | DAP II - Microsoft 365 + IoT based data acquisition | Publishing and hosting of real-time DisCo load offtake performance on NERC website - TCN 33kV IoT | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
PRS | DAP II - Microsoft 365 + IoT based data acquisition | Publishing and hosting of real-time grid performance on NERC website - Captive and Offgrid GenCos | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Metering for all within 3 years | Implement MOU with NINAS for accreditation of Meter Test Laboratories across the country. Monthly status report. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Sustained growth in availability and quality of supply | Ensure the establishment of a comprehensive scope for SCADA/EMS, covering the World Bank & TCN’s IGR scope of work. Monthly status report on the deployment of SCADA in NESI | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Sustained growth in availability and quality of supply | Ensure the SO implements the functionality test for power plants in accordance with the Grid Code. Quarterly compliance reporting. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Sustained growth in availability and quality of supply | Develop a database and monitor GenCos’ 5-year capacity recovery and expansion plans. Quarterly report on the ramp-up of power generation trajectories | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Sustained growth in availability and quality of supply | Develop guidelines and track relay coordination programs across GX /TX/DX interface. Quarterly report on compliance with relay coordination program in NESI | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Sustained growth in availability and quality of supply | Study Harmonics and its effect on ATC&C losses, power quality, and system reliability. Quarterly report | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Effective compliance monitoring and enforcement | Ensure the SO establishes a coordinated maintenance schedule across the subsectors of the NESI. NESI maintenance database. Quarterly compliance report | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Effective compliance monitoring and enforcement | Conclude the review of the operating codes and NESIS, Regulations. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Effective compliance monitoring and enforcement | Monitor for compliance with the provisions of the operating codes and NESIS regulation (Code activation) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Effective compliance monitoring and enforcement | Training for manpower development to enhance the EPM division’s output and organizational productivity | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Enhancement of security of power supply | Review the Generation Adequacy Report alongside Transmission and Distribution expansion plans that will guide investment in NESI. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Enhancement of security of power supply | Comprehensive technical studies on the integration of VRE into the national power grid; Grid adequacy report for VRE integration | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Enhancement of security of power supply | Investigation of grid system collapses that occurred in 2022. Report on solutions to grid stability and reliability | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Enhancement of security of power supply | Technical audit of the distribution network; Report on the condition of the network across the Discos. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Enforcement of safety standards | Review, approve, and monitor the implementation of the licensee’s accident reduction strategy document. Quarterly report on the implementation status of the strategy. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Enforcement of safety standards | Develop operational guidelines for TSO & DSO. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
EPM | Promotion of local content and human resources development in NESI | Review existing documents/Regulations and develop a framework for implementation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Review of Existing Regulations |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Impact of Constitutional Amendment on NESI |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Development of Practice directions for NESI |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Seminar for Judges |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Finalization of pending Orders due in the Strategic Plan |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Precedence and Boilerplates for Internal Contracts |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Winding down of NBET Operations and Novation’s for PPAS |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Training of Members of Dispute Resolution Panel. |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Development of Standard Operating Procedures and Workplan for each type of Approvals issued by the Commission. |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Automation of Licensing Process |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
LLC | Implementation of a Monitoring and Enforcement Framework for Compliance |  | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Performance Management System | Commission’s approval of new process. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Performance Management System | Training of supervisors and subordinates on the implementation of the new performance management system. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Performance Management System | Commence Implementation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Recruitment of new employees. | Personality Test and interview | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Recruitment of new employees. | Compile result/outcome of the interviews to the Commission | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Recruitment of new employees. | Consideration and approval of successful candidates | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Recruitment of new employees. | Commission to approve the release of appointment letters to the successful candidates | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Recruitment of new employees. | Notification of successful candidates | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Onboarding of new employee | Welcoming the new Employee and integrating them seamlessly into the system. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Onboarding of new employee | Providing conducive working environment and assigning work tools. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Onboarding of new employee | Ensuring Setling down of the new recruits in their offices and assigning them mentors . | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Onboarding of new employee | Formal trainings on NERC cultures and values, as well as soft skills development work processes. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Onboarding of new employee | Training on basic regulatory knowledge | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | HRD Software | Development of ToR | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | HRD Software | Engagement of Consultant through the procurement process to provide the software and training staff on its implementation. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | HRD Software | Implementation of the new automated process. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Staff Capacity Development | Critical analysis and determination of skills gap, including soft skills development. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Staff Capacity Development | Identification of relevant training needs. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Staff Capacity Development | Finding credible training firms to deliver the required capacity development. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Staff Capacity Development | Obtaining Commission’s of the training plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Staff Capacity Development | Implementation of the training plan. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Promotion Exercise | Approval for the exercise | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Promotion Exercise | Promotion Examination | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Promotion Exercise | Notification of successful candidates and Issuance of Promotion Letters | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Infrastructure Management | Configuration & Deployment of newly purchased tools(laptops and printers) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Infrastructure Management | Purchase of New Laptops | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Infrastructure Management | Submission of Specifications | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Infrastructure Management | Procurement Process | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Infrastructure Management | Configuration & Issuance | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Purchase of New Servers, firewall, Storage & Printers | Submission of Specifications | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Purchase of New Servers, firewall, Storage & Printers | Procurement Process | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Purchase of New Servers, firewall, Storage & Printers | Configuration & Issuance | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of Wireless Network Infrastructure | Submission of Specifications | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of Wireless Network Infrastructure | Procurement Process | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of Wireless Network Infrastructure | Deployment | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of IP Phones | Submission of Specifications | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of IP Phones | Procurement Process | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of IP Phones | Deployment | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Back Up Power | Submission of Specifications | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Back Up Power | Procurement Process | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Back Up Power | Deployment | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Project Work S.A.F.E (PWS) | PWS - Document Management System | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Project Work S.A.F.E (PWS) | Automated licensing processing system | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Project Work S.A.F.E (PWS) | Electronic correspondence management system | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | PWS - Optimisation of M365 for Data Management & Visualisation. | Intranet Portal | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | PWS - Optimisation of M365 for Data Management & Visualisation. | Staff Onboarding Porta | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | PWS - Optimisation of M365 for Data Management & Visualisation. | Work Process Automation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Services Management | Management Of Contracts for ICT Services | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Services Management | Maintenance & Repairs of ICT Equipments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Purchase of ICT Consumables | Develop Specifications | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Purchase of ICT Consumables | Procurement Process | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT User Support | Service Desk Management | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT User Support | Website update & maintenance | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | User Skills Enhancement (USE) | USE 1 | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | User Skills Enhancement (USE) | USE 2 | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | User Skills Enhancement (USE) | USE 3 | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | User Skills Enhancement (USE) | USE 4 | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | User Skills Enhancement (USE) | USE 5 | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | User Skills Enhancement (USE) | USE 6 | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Solutions Support | Management of Access Control system | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Solutions Support | Provide ICT support for Promotion examination | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Solutions Support | Provide ICT support for Recruitment Exercise | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Projects & Support | Website Redesign | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Solutions Support | Business Continuity Plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Solutions Support | Disaster Recovery Plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Solutions Support | Cyber Resilience plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Solutions Support | NESI Cyber Security Workshop | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Governance | NDPR 2019 Audit | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Governance | COBIT v5 Implementation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | ICT Governance | ITIL v4 Implementation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of 4Nos. Elevators in NERC Headquarters Building | Secure BPP "No Objection" for Retrictive Tender | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of 4Nos. Elevators in NERC Headquarters Building | RFP & Technical Evaluation of Bid | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of 4Nos. Elevators in NERC Headquarters Building | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of 4Nos. Elevators in NERC Headquarters Building | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of 4Nos. Elevators in NERC Headquarters Building | NTB or MoP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of 4Nos. Elevators in NERC Headquarters Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Replacement of 4Nos. Elevators in NERC Headquarters Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for NERC HQ Building | Advert / Invitation to Tender | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for NERC HQ Building | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for NERC HQ Building | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for NERC HQ Building | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for NERC HQ Building | NTB or MoP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for NERC HQ Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for NERC HQ Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Completion of Partition & Furnishing of NERC Headquarters Building 4th, 5th, 6th & G-Floors | Project Execution and Payments on-going | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of VRV AC System of floors 6th ,5th ,4th, 3rd, 2nd,1st & G-Floors of NERC Headquaters Building | Project Execution and Payments on-going | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Water Fountain NERC Headquarters Building | RFQs or Advert | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Water Fountain NERC Headquarters Building | ICT Solutions Support | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Water Fountain NERC Headquarters Building | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Water Fountain NERC Headquarters Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Water Fountain NERC Headquarters Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fencing and Gate at NERC Makurdi Land in Benue State | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fencing and Gate at NERC Makurdi Land in Benue State | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fencing and Gate at NERC Makurdi Land in Benue State | Chairman Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fencing and Gate at NERC Makurdi Land in Benue State | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fencing and Gate at NERC Makurdi Land in Benue State | Chairman Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fencing and Gate at NERC Makurdi Land in Benue State | Award of Contract and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fencing and Gate at NERC Makurdi Land in Benue State | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Repair of NERC Headquarters Building Basement | NTB Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Repair of NERC Headquarters Building Basement | Award of Contract and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Repair of NERC Headquarters Building Basement | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Document Management System (DocStream) for NERC | Project Execution and Payments on-going | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Lot 10 Partition & Furnishing of NERC Headquarters Building G-Floor & Kitchenette | Memo to Chairman/Comm F&MS/Procurement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Lot 10 Partition & Furnishing of NERC Headquarters Building G-Floor & Kitchenette | Review with Contractor | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Lot 10 Partition & Furnishing of NERC Headquarters Building G-Floor & Kitchenette | NTB Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Lot 10 Partition & Furnishing of NERC Headquarters Building G-Floor & Kitchenette | Award of Contract and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Lot 10 Partition & Furnishing of NERC Headquarters Building G-Floor & Kitchenette | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Furnishing and Office Appliances for 35 NERC Forum Offices | Advert / Invitation to Tender | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Furnishing and Office Appliances for 35 NERC Forum Offices | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Furnishing and Office Appliances for 35 NERC Forum Offices | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Furnishing and Office Appliances for 35 NERC Forum Offices | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Furnishing and Office Appliances for 35 NERC Forum Offices | NTB or MoP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Furnishing and Office Appliances for 35 NERC Forum Offices | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Furnishing and Office Appliances for 35 NERC Forum Offices | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for 35 NERC Forum Offices | Advert / Invitation to Tender | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for 35 NERC Forum Offices | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for 35 NERC Forum Offices | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for 35 NERC Forum Offices | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for 35 NERC Forum Offices | NTB or MoP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for 35 NERC Forum Offices | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Solar Power System for 35 NERC Forum Offices | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Engagement of Facilities Manager for HERC Headquarters Building | Advert / Invitation to Tender | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Engagement of Facilities Manager for HERC Headquarters Building | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Engagement of Facilities Manager for HERC Headquarters Building | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Engagement of Facilities Manager for HERC Headquarters Building | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Engagement of Facilities Manager for HERC Headquarters Building | NTB or MoP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Engagement of Facilities Manager for HERC Headquarters Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Engagement of Facilities Manager for HERC Headquarters Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fire Exit Doors in all Wings/Basement of NERC HQ Building | Advert / Invitation to Tender | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fire Exit Doors in all Wings/Basement of NERC HQ Building | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fire Exit Doors in all Wings/Basement of NERC HQ Building | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fire Exit Doors in all Wings/Basement of NERC HQ Building | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fire Exit Doors in all Wings/Basement of NERC HQ Building | NTB or MoP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fire Exit Doors in all Wings/Basement of NERC HQ Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Fire Exit Doors in all Wings/Basement of NERC HQ Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | Memo to Chairman/Comm F&MS/Procurement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | Chairman Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | Chairman Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Safety Animation Video NERC HQ Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | Memo to Chairman/Comm F&MS/Procurement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | Chairman Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | Chairman Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Provision of Security Canopy and Porta Cabin for security/driver/cleaning Personnel | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Procurement of Project Vehicles | Advert / Invitation to Tender | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Procurement of Project Vehicles | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Procurement of Project Vehicles | NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Procurement of Project Vehicles | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Procurement of Project Vehicles | NTB or MoP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Procurement of Project Vehicles | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Procurement of Project Vehicles | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | Memo to Chairman/Comm F&MS/Procurement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | Chairman Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | Chairman Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Continous Improvement of NERC Headquarters Building (As need arises) | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | Memo to Chairman/Comm F&MS/Procurement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | Chairman Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | Chairman Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of two (2) units of 1000kVA generators by Mantrac | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | Memo to Chairman/Comm F&MS/Procurement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | Chairman Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | Chairman Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of VRV A/C system | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | BPP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Chairman or NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Chairman or NTB Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | BPP Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Chairman or NTB Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Chairman or NTB Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Security Services in NERC HQ Building | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | Memo to Chairman/Comm F&MS/Procurement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | RFQs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | Chairman Approval of Technical Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | Financial Bid Opening & Evaluation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | Chairman Approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | Award of Contact and Signing | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Maintenance of Current (old) Elevators | Project Execution and Payments | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2023 Budget Performance | 1st Quarter | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2023 Budget Performance | 2nd Quarter | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2023 Budget Performance | 3rd Quarter | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2023 Budget Performance | 4th Quarter | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2024 Budget | Budget Execution and performance Monitoring | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2024 Budget | Preparation of 2024 Budget Proposal | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2024 Budget | Submission of 2024 Budget Proposal to Stakeholders | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Revenue | Revenue monitoring and updating | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Expenditure | Vendor and Staff Claims | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Payroll | Monthly salary | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Statutory Remittances | Pensions | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Statutory Remittances | Tax returns | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Account Reconcilliation | CBN TSA | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | Account Reconcilliation | CBN Domicilliary | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2022 Audit of Commission's Account | Commencement of 2022 Audit of Commission's account | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
FMS | 2022 Audit of Commission's Account | Finalization of 2022 Audit of Commission's account | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Transferring Compliants Resolution Meetings to DisCos | 2023 Q1 | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Transferring Compliants Resolution Meetings to DisCos | Collate submission from DisCos | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Transferring Compliants Resolution Meetings to DisCos | Cordinate submission for Commission's consideration and request approval for Forum Secretaries participation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Transferring Compliants Resolution Meetings to DisCos | Paricipation of Forum Secretaties in Complaints Resolution Meetings | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Transferring Compliants Resolution Meetings to DisCos | Submission of quartely Reports | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Customer Enumeration - Strategic Partnership with National Population Commission on 2023 Census | Meeting with NPC | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Customer Enumeration - Strategic Partnership with National Population Commission on 2023 Census | Preparation and approval of conecpt note | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Customer Enumeration - Strategic Partnership with National Population Commission on 2023 Census | Development of MOU | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Customer Enumeration - Strategic Partnership with National Population Commission on 2023 Census | Signing of MOU | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Customer Enumeration - Strategic Partnership with National Population Commission on 2023 Census | Implementation of MOU | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Customer Enumeration - Strategic Partnership with National Population Commission on 2023 Census | Report | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Prepare Call Center Implementation Plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Constitution of Project Implementation Committee | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Request for data with respect to Discos’ Call Center | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Inception Meeting with Consultant | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Development of FAQs, complaint categories, training materials etc. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Development and implementation of Awareness Campaign Plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Organize virtual interactive with Representatives of DISCOs | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Organize Training for Call Agents and specific NERC Staff | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Call Center Configuration | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | CRM configuration | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Call Centre Implementation | Commissioning of Call Center | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Office Publicity - Airing of Jingles | Request for most listened Radio Statations and Cost from Forum Sec | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Office Publicity - Airing of Jingles | Collate report and send to PAD | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Office Publicity - Airing of Jingles | PAD to make submission and resquest for Commission approval for Airing of Jingles | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Office Publicity - Airing of Jingles | Develop metrics for monitoring and measuring impact of jingles | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Office Publicity - Airing of Jingles | Monitoring airing of Jingles | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Office Publicity - Airing of Jingles | Quarterly Report | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Office Publicity - Airing of Jingles | Quaterly Report | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Member Training | Selection of Forum Members to be Trained | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Member Training | Preparation and approval of Implementation Memo | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CA | Forum Member Training | Logistics and Implementation of Training | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Desktop Research on Trading License Requirements | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Develop Commercial Requirements for Trading Licence - Amendment of Schedule F | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Internal Review of Commercial Requirements | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Submit recommended Commercial Requirements to LL&C | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Post approved consultation paper on website | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Receipt and Review of inputs from Stakeholders | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Conduct the cosultation across the geopolitical zones | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Review outcome of the Consultation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Review the regulation based on outcome of the consultation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of Trading Licence Requirements in the Existing Licensing Regulation (schedule 1F) | Post the reviewed regulation on the website with amended Schedule F | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Nomination and Set up of stakeholder committee - MRRT (Driven by the iSAP/MO) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | First Meeting of MRRT | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Second Meeting of MRRT | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Third Meeting of MRRT | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Response from DISCOS in respect of amendment of the Rules to include Escrow Account Administration | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Circulation of the Letter to iSAP members for review | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Submission of iSAP's position on item 5 to the Commisison | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Meeting of iSAP and MRRT to review amendment submission | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Final review of Amended Document | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Amendment of the Market Rules | Submission of Amended Document to the Commission for approval | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Review of Security Challenges and the resultant Revenue losses in the NESI | Update and present the framework to address the challenges | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Review of Security Challenges and the resultant Revenue losses in the NESI | Invite the Consultant to present and discuss the proposal on the assessment of risk level and implementation framework with the Commission | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Review of Security Challenges and the resultant Revenue losses in the NESI | Engaging the relevant stakeholders (BPE, ONSA, FMP, etc) to discuss framework and the consultant proposal | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Review of Security Challenges and the resultant Revenue losses in the NESI | Seek NERC/BPE approval of the finalized framework to begin implementation. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Review of Security Challenges and the resultant Revenue losses in the NESI | Communicate the Discos, the NERC/BPE approved framework to address security challenges | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Monitoring of world Bank/PSRO performance indicator for compliance with Disbursement Linked Indicator (DLI) | Keeping track of DLR/DLI deliverables and timeline. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Monitoring of world Bank/PSRO performance indicator for compliance with Disbursement Linked Indicator (DLI) | Receive progress report from the relevant task officers regarding the DLRs/DLIs and discuss challenges that may affect deadlines. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Monitoring of world Bank/PSRO performance indicator for compliance with Disbursement Linked Indicator (DLI) | Liaising with the PSRO office(r) to discuss progress and challenges. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Monitoring of world Bank/PSRO performance indicator for compliance with Disbursement Linked Indicator (DLI) | Gather and submit all data requested by PSRO office for validity verification of DLRs/DLIs requirement. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Implementation of Regulatory netoffs and monitoring of credit notes issued to Discos | Submission of reviewed data from NBET. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Implementation of Regulatory netoffs and monitoring of credit notes issued to Discos | Meetings with NBET. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Implementation of Regulatory netoffs and monitoring of credit notes issued to Discos | Computation of Tariff shortfall and share of MO and NBET share of Tariif shortfall | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
MCR | Implementation of Regulatory netoffs and monitoring of credit notes issued to Discos | Submission of the computed figures and memo to VC. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Process & Risk Audit | Chairman's Office Division | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Process & Risk Audit | Legal, Licensing & Compliance Division | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Process & Risk Audit | Engineering & Performance Monitoring Division | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Public Enlightenment | Public enlightenment on Energy Cap | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Quarterly Media Briefings | Media Briefing (1) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Quarterly Media Briefings | Media Briefing (2) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Quarterly Media Briefings | Media Briefing (3) | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Targeted Media Campaigns | Media Campaign on Investments in the Network | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Targeted Media Campaigns | Secure Commission's approval for campaign implementation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Targeted Media Campaigns | Get approval for communication script and implementation plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Targeted Media Campaigns | Develop messaging and creatives | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Targeted Media Campaigns | Start media campaign | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Targeted Media Campaigns | Media Campaign on Power Sector Revovery Program | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Targeted Media Campaigns | Get approval for communication script and implementation plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Engagement with NASS on the power sector | Targeted engagement with NASS | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Engagement with NASS on the power sector | Get Commission's approval for engagement, theme and budget for NASS engagement | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Engagement with NASS on the power sector | Send out an invitation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Engagement with NASS on the power sector | Implementation | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Procurement of goods, works and services in support of the Commission's 2023 workplan | Constitution of a Procurement Planning Committee ("PPC") | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Procurement of goods, works and services in support of the Commission's 2023 workplan | Development of an efficient procurement plan by PPC in conjunction with the Procurement Unit | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Procurement of goods, works and services in support of the Commission's 2023 workplan | Identification of needs (goods, work and consultancy) assessment & cost estimates | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Procurement of goods, works and services in support of the Commission's 2023 workplan | Approval of the 2023 Procurement Plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Procurement of goods, works and services in support of the Commission's 2023 workplan | Implementation of the procurement plan | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Board Co-ordination | Co-ordination of the Commission's formal meetings as a board and the meetings of the Commission as a board with licensees and other stakeholders | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Vital Records/Information Management | Record-keeping, safe custody, effective communication, management and retrieval of the Commission's vital records | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | NERC FOI Desk | Annual FOI report to the Ministry of Justice | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | NERC FOI Desk | Co-ordination/tracking of requests/management of processes under the Freedom of Information Act | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Administrative proceedings/Hearings | Hearing Registry for administrative proceedings/hearings - LLC led | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Corporate Governance of NESI ("Fit & Proper" assessment) | KYL Assessment Secretariat for determination of persons holding key management positions in licensee companies as "fit & proper" - LLC led | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Review and oversight of DRP Processes | Review and oversight of DRP processes to align with expectations of NESI - LLC led | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Review and oversight of DRP Processes | Initial Meeting with DRC on revised process for DRP | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Review and oversight of DRP Processes | Review of initial submission by the DRC on revised process for DRP | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Review and oversight of DRP Processes | Review of updated submission by DRC | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Review and oversight of DRP Processes | Training of DRP members | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | NESI Meetings | NESI Meeting Secretariat - PRS led | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Resolution of Appeals from Forum Offices | Support to Inter Divisional Committee on the Resolution of Appeals ("IDCRA") - CA led | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Resolution of Appeals from Forum Offices | Development of template/guidance for formal responses on decisions on appeal | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Resolution of Appeals from Forum Offices | General support to CA for review and finalisation of written processes | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Review of current regulations | Support for the process of reviewing current regulations - LLC led | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE
CO | Review of current regulations | Categorisation of regulations into buckets - Ok as is, relevant but requires review and no longer relevant. | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE